## To-Do List
Virtual CPA2B Event Checklist
TASK | PRIORITY | STATUS | START DATE | DUE DATE | % COMPLETE | DONE? | NOTES
Set up Zoom account or request from TXCPA | Normal | Not Started | 2020-12-25 | 2021-01-01 | 0% | 0
Decide on 1 or 2 day event | Normal | In Progress |  |  | 0% | 0
Select date(s) for event | Normal | Complete |  |  | 0% | 0
Contact speakers to confirm their schedule | Normal | In Progress |  |  | 0% | 0
Send Educator promo | Normal | In Progress |  |  | 0%
Outreach to faculty & student ambassadors in your area | Normal | In Progress |  |  | 0%
Send Announcement to students | Normal | In Progress |  |  | 0% |  | 6-8 weeks prior to event
Social post - Announcement | Normal | In Progress |  |  | 0%
Send Reminder email #1 to students | Normal | In Progress |  |  | 0% |  | 2 weeks post announcement
Social post - Highlight session topics | Normal | In Progress |  |  | 0%
Send Reminder email #2 to students | Normal | In Progress |  |  | 0% |  | 4 weeks post announcement
Social post - 5 reasons to attend | Normal | In Progress |  |  | 0%
Send Reminder email #3 to students | Normal | In Progress |  |  | 0% |  | 6 weeks post announcement
Social post - Testimonies from previous attendees (if applicable) | Normal | In Progress |  |  | 0%
Send Final Reminder to students | Normal | In Progress |  |  | 0% |  | Week prior to event
Social post - Last call | Normal | In Progress |  |  | 0%
Send What You Need to Know email to registrants | Normal | In Progress |  |  | 0% |  | 2-3 days prior to event
Thank you to participants | Normal | In Progress |  |  | 0% |  | 2-3 days after the event